DIASPORA VOTE COMMITTEE
SUGGESTED TIMELINE TO E.C. FOR THE DEVELOPMENT OF REGULATIONS FOR THE PEOPLES' REPRESENTATION ACT, 699 (ROPAA, 2006) AND DIASPORANS VOTING IN 2008 ELECTIONS.
 

1.      Completion of Implementation Guidelines (REGULATIONS) December 2006
2.       Final ROPAA Guidelines to Parliament for Approval

December ‘06
3.        Education campaign on ROPAA



 January 2007
4.        EC Mailing of Registration forms to Embassies/Consulates
 January ‘07

5.         Ghanaians requesting and/or picking up registration forms
 January ‘07
6.          Registration Period (IN-PERSON and POSTAL)

January ‘07thru June         ‘07 –June 30 ‘07 (Closing date)

7.          Verification & Certification of Registration Roster
& Issue of Voter ID cards  July ’07 thru December ‘07

8.         Completion of Mailing of Voter ID Cards to Embassies/Consulates by EC
 January 2008
9.        Completion of Mailing of Voter ID cards to Registrants by Embassies March ‘08

10.    Printing of Overseas ballots in Ghana and mailing to Embassies via diplomatic pouch by EC – Completed by June ‘08
11.      Completion of Mailing of ballots to Postal Voters through the Embassies/Consulates October ‘08

12.      Voters Return of POSTAL VOTING Ballots to Embassies latest 
October 31 ‘08

13.      VOTING: IN- PERSON at Embassies/Consulates on November 6 and 7 ‘08
14.      Counting of Votes/Transmittal of vote tallies to EC in Ghana on Election Day November ‘0 8

1.
 Need a list of countries where Ghana has embassies and consulates 
2.
Formation of Committees to witness the counting and transmittal of ballots

3.
Arrangement with national electoral management bodies to supervise elections

 SUBMITTED BY:
 Dr. Agyenim Boateng

 Benjamin. Afrifa
FOR: DIASPORAN VOTERS COMMITTEE (DVC)

April 18, 2008
